## Inputs
Noriva 90-Day Turnaround Plan
Day range | Workstream | Finding | Action | Owner | Due date | KPI | Status
1-15 | Cash and controls | Validate daily cash | Introduce close checklist | Finance | 46037 | Cash variance | Not started
16-30 | Menu | Identify low contribution items | Complete menu engineering | Operations | 46052 | Contribution/item | Not started
31-60 | Labor | Align rota to demand | Rebuild staffing curve | GM | 46082 | Labor % | Not started
61-90 | Growth | Test one offer | Run controlled campaign | Marketing | 46112 | Incremental contribution | Not started

## Summary
Noriva 90-Day Turnaround Plan
Metric | Result
Rows entered | 4

## Instructions
Noriva 90-Day Turnaround Plan
How to use this workbook
1 | Replace sample rows with your verified business data.
2 | Yellow and blue-font cells are intended for user inputs; calculated cells contain formulas.
3 | Review the Summary after completing the input table.
4 | Do not use sample values as market facts or investment advice.